## Forward Traceability
Requirements | Tests | Executions | Defects
AAFP-49 - API TESTE CASES | AAFP-50 - [POST] Save employee | API Testing cycle - PASS | None
AAFP-49 - API TESTE CASES | AAFP-51 - [POST] Add employee work experience | API Testing cycle - PASS | None
AAFP-49 - API TESTE CASES | AAFP-52 - [GET] Employee Details | API Testing cycle - PASS | None
AAFP-49 - API TESTE CASES | AAFP-53 - [PUT] Update employee work experience | API Testing cycle - PASS | None
AAFP-49 - API TESTE CASES | AAFP-54 - [PUT] EDIT employee work experience when record is missing | API Testing cycle - PASS | None
AAFP-49 - API TESTE CASES | AAFP-55 - [DEL] Delete Employee work experience | API Testing cycle - PASS | None
AAFP-48 - The user can add numbers in the middle name - 1 defect | AAFP-12 - Enter invalid data in Middle Name" - optional fields | Ad hoc - FAIL | AAFP-48 - In Progress - The user can add numbers in the middle name
AAFP-48 - The user can add numbers in the middle name - 1 defect | AAFP-12 - Enter invalid data in Middle Name" - optional fields | Ad hoc - FAIL | AAFP-48 - In Progress - The user can add numbers in the middle name
AAFP-47 - The user can't use down arrow key to select any option from Blood Type dropdown button - 1 defect | AAFP-27 - Drop down of Blood type field should be scrolled down by clicking down arrow key of the keyboard. | Ad hoc - FAIL | AAFP-47 - In Progress - The user can't use down arrow key to select any option from Blood Type dropdown button
AAFP-47 - The user can't use down arrow key to select any option from Blood Type dropdown button - 1 defect | AAFP-27 - Drop down of Blood type field should be scrolled down by clicking down arrow key of the keyboard. | Ad hoc - FAIL | AAFP-47 - In Progress - The user can't use down arrow key to select any option from Blood Type dropdown button
AAFP-46 - The drop down button for Blood Type shows only 6 options - 1 defect | AAFP-26 - Verify the dropdown list for Blood Type to display a list containing values | Ad hoc - FAIL | AAFP-46 - Backlog - The drop down button for Blood Type shows only 6 options
AAFP-46 - The drop down button for Blood Type shows only 6 options - 1 defect | AAFP-26 - Verify the dropdown list for Blood Type to display a list containing values | Ad hoc - FAIL | AAFP-46 - Backlog - The drop down button for Blood Type shows only 6 options
AAFP-45 - The user can add more than 200 characters to "comment" field from Add attachment section - 1 defect | AAFP-36 - Check that "Comment" field allows maxim 200 characters. | Ad hoc - FAIL | AAFP-45 - Backlog - The user can add more than 200 characters to "comment" field from Add attachment section
AAFP-45 - The user can add more than 200 characters to "comment" field from Add attachment section - 1 defect | AAFP-36 - Check that "Comment" field allows maxim 200 characters. | Ad hoc - FAIL | AAFP-45 - Backlog - The user can add more than 200 characters to "comment" field from Add attachment section
AAFP-44 - "Last Name" field accept over 30 characters - 1 defect | AAFP-18 - Verify that "Last Name" field accept over 30 characters | Ad hoc - FAIL | AAFP-44 - Backlog - "Last Name" field accept over 30 characters
AAFP-44 - "Last Name" field accept over 30 characters - 1 defect | AAFP-18 - Verify that "Last Name" field accept over 30 characters | Ad hoc - FAIL | AAFP-44 - Backlog - "Last Name" field accept over 30 characters
AAFP-43 - The user can't use down arrow key to select any option from Nationality dropdown button - 1 defect | AAFP-20 - Drop down of Nationality field should be scrolled down by clicking down arrow key of the keyboard. | Ad hoc - FAIL | AAFP-43 - Backlog - The user can't use down arrow key to select any option from Nationality dropdown button
AAFP-43 - The user can't use down arrow key to select any option from Nationality dropdown button - 1 defect | AAFP-20 - Drop down of Nationality field should be scrolled down by clicking down arrow key of the keyboard. | Ad hoc - FAIL | AAFP-43 - Backlog - The user can't use down arrow key to select any option from Nationality dropdown button
AAFP-42 - The birthday field accept future date - 1 defect | AAFP-16 - Verify if employee birthday can't be set to future date | Ad hoc - FAIL | AAFP-42 - Backlog - The birthday field accept future date
AAFP-42 - The birthday field accept future date - 1 defect | AAFP-16 - Verify if employee birthday can't be set to future date | Ad hoc - FAIL | AAFP-42 - Backlog - The birthday field accept future date
AAFP-41 - The user can select both values for the same issue - 1 defect | AAFP-21 - Verify that only one value from the radio buttons can be selected | Ad hoc - FAIL | AAFP-41 - Backlog - The user can select both values for the same issue
AAFP-41 - The user can select both values for the same issue - 1 defect | AAFP-21 - Verify that only one value from the radio buttons can be selected | Ad hoc - FAIL | AAFP-41 - Backlog - The user can select both values for the same issue
AAFP-40 - Driver's License Number is not be visible on the page. - 1 defect | AAFP-14 - Check the "Driver's License Number" optional fields | Ad hoc - FAIL | AAFP-40 - Backlog - Driver's License Number is not be visible on the page.
AAFP-40 - Driver's License Number is not be visible on the page. - 1 defect | AAFP-14 - Check the "Driver's License Number" optional fields | Ad hoc - FAIL | AAFP-40 - Backlog - Driver's License Number is not be visible on the page.
AAFP-39 - User can delete more than one attachment from attachment list - 1 defect | AAFP-35 - Check that user can delete many attachment from attachment list | Ad hoc - FAIL | AAFP-39 - Backlog - User can delete more than one attachment from attachment list
AAFP-39 - User can delete more than one attachment from attachment list - 1 defect | AAFP-35 - Check that user can delete many attachment from attachment list | Ad hoc - FAIL | AAFP-39 - Backlog - User can delete more than one attachment from attachment list
AAFP-38 - User is not allow to add multiple uploads in the same time - 1 defect | AAFP-33 - Check if multiple uploads are allowed | Ad hoc - FAIL | AAFP-38 - In Progress - User is not allow to add multiple uploads in the same time
AAFP-38 - User is not allow to add multiple uploads in the same time - 1 defect | AAFP-33 - Check if multiple uploads are allowed | Ad hoc - FAIL | AAFP-38 - In Progress - User is not allow to add multiple uploads in the same time
AAFP-37 - Save Button don't save any information - 1 defect | AAFP-29 - Check the functionality of "Save" button | Ad hoc - FAIL | AAFP-37 - In Progress - Save Button don't save any information
AAFP-37 - Save Button don't save any information - 1 defect | AAFP-29 - Check the functionality of "Save" button | Ad hoc - FAIL | AAFP-37 - In Progress - Save Button don't save any information
AAFP-30 - Add attachment section in New Employee page | AAFP-31 - Check the functionality of "Edit" button | Ad hoc - PASS | None
AAFP-30 - Add attachment section in New Employee page - 1 defect | AAFP-33 - Check if multiple uploads are allowed | Ad hoc - FAIL | AAFP-38 - In Progress - User is not allow to add multiple uploads in the same time
AAFP-30 - Add attachment section in New Employee page - 1 defect | AAFP-36 - Check that "Comment" field allows maxim 200 characters. | Ad hoc - FAIL | AAFP-45 - Backlog - The user can add more than 200 characters to "comment" field from Add attachment section
AAFP-30 - Add attachment section in New Employee page | AAFP-32 - Check that user can add one attachments | Ad hoc - PASS | None
AAFP-30 - Add attachment section in New Employee page - 1 defect | AAFP-35 - Check that user can delete many attachment from attachment list | Ad hoc - FAIL | AAFP-39 - Backlog - User can delete more than one attachment from attachment list
AAFP-30 - Add attachment section in New Employee page | AAFP-34 - Check that user can delete an attachment from attachment list | Ad hoc - PASS | None
AAFP-23 - Custom Fields section in "New employee" page - 1 defect | AAFP-29 - Check the functionality of "Save" button | Ad hoc - FAIL | AAFP-37 - In Progress - Save Button don't save any information
AAFP-23 - Custom Fields section in "New employee" page | AAFP-25 - Check the functionality of "Edit" button | Ad hoc - PASS | None
AAFP-23 - Custom Fields section in "New employee" page - 1 defect | AAFP-27 - Drop down of Blood type field should be scrolled down by clicking down arrow key of the keyboard. | Ad hoc - FAIL | AAFP-47 - In Progress - The user can't use down arrow key to select any option from Blood Type dropdown button
AAFP-7 - Personal details section in "New employee" page | AAFP-9 - Check the "First name" required fields by not filling any data | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page | AAFP-10 - Check the "Last Name" required fields by not filling any data | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page | AAFP-28 - Check the functionality of "Save" button | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page | AAFP-13 - Check the "First Name" and "Last Name" required fields | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page | AAFP-15 - Verify any optional fields are not mandatory when submitting the registration request to the server | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page | AAFP-24 - Check the functionality of "Edit" button | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page - 1 defect | AAFP-12 - Enter invalid data in Middle Name" - optional fields | Ad hoc - FAIL | AAFP-48 - In Progress - The user can add numbers in the middle name
AAFP-7 - Personal details section in "New employee" page - 1 defect | AAFP-16 - Verify if employee birthday can't be set to future date | Ad hoc - FAIL | AAFP-42 - Backlog - The birthday field accept future date
AAFP-7 - Personal details section in "New employee" page | AAFP-17 - Verify that New Employee date of birth accepts only dd/ mm/yyyy format | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page - 1 defect | AAFP-20 - Drop down of Nationality field should be scrolled down by clicking down arrow key of the keyboard. | Ad hoc - FAIL | AAFP-43 - Backlog - The user can't use down arrow key to select any option from Nationality dropdown button
AAFP-7 - Personal details section in "New employee" page - 1 defect | AAFP-21 - Verify that only one value from the radio buttons can be selected | Ad hoc - FAIL | AAFP-41 - Backlog - The user can select both values for the same issue
AAFP-7 - Personal details section in "New employee" page | AAFP-22 - Check the navigation between the fields is successful using tab key | Ad hoc - PASS | None
AAFP-7 - Personal details section in "New employee" page - 1 defect | AAFP-14 - Check the "Driver's License Number" optional fields | Ad hoc - FAIL | AAFP-40 - Backlog - Driver's License Number is not be visible on the page.
AAFP-7 - Personal details section in "New employee" page - 1 defect | AAFP-18 - Verify that "Last Name" field accept over 30 characters | Ad hoc - FAIL | AAFP-44 - Backlog - "Last Name" field accept over 30 characters
AAFP-6 - As a user I want to be able to add personal details for "New employee" section | None | None | None